## Sheet1
T-10 Bearing Timeline
Date | Event | Results/Action Items
2003-03-01 | First Reference on tin flashed bearing | Test mild on lead
2003-04-01 | Meeting in San Antonio - April 21 | Decision to investigate possibly making new batch of bearings to match original bearings
2003-05-07 | Teleconference - May 7 | Decision to have 1200 pairs of T10 bearings made to match original bearings - Part Number 62GB2403
2003-06-25 | Bearings Received at TEI | TEI inspects and ships bearings to labs for testing
2003-08-01 | First two runs on 62GB2403 | Lead Results 12 and 16
2003-09-01 | Third run on 62GB2403 | Lead result 9 ; intercooler leak
2003-09-01 | TEI sends one pair each new style and old style to Mack for supplier analysis | Mack sends to supplier for analysis
2003-10-01 | Fourth run on 62GB2403 | Lead result 12 ; intercooler leak
2003-10-01 | Meeting in Paulsboro - October 23 | Ken presents data showing lead content in flash plate lower than target. Decision made to run with "unflashed" bearings Part Number 62GB2404
2003-11-01 | Fifth Run on 62GB2403 | Lead result 12
2003-11-01 | Unflashed rod bearings shipped to labs and TEI (18 to labs and 42 to TEI) | Lead results 6, 8, and 29. The run with 29 ran with old style main bearings
2003-12-01 | Decision made to have another batch made with 100% lead in flash plate | Mack to work with supplier to have batch made with 100% lead flash plate
2004-01-01 | TEI receives 62GB2405 bearings and distributes to the labs. | One test completes with 26 lead
2004-02-01 | Two additional tests complete on 62GB2405 | Lead results 12 and 8
2004-02-01 | Meeting in San Antonio - February 12 | Reviewed all test results. No real conclusions. Lubrizol agrees to analyze bearings with a "bluish" tint to them
2004-02-01 | Teleconference - February 27 | Lubrizol presents their initial analysis of 62GB2405 bearings with "bluish" tint. Analysis included a new bearing and bearings from each of the three runs (see analysis dated 2/27/04). TEI to send old style bearings from previous batches to Lz for comparison analysis.
2004-03-01 | Teleconference - March 15 | Lubrizol presents a more detailed analysis of the 100% lead bearings and the old style bearings sent to them by TEI. Dana presents overview of how bearings are made and the composition of the preservation oil. They agree to perform additional analysis.
2004-03-01 | Teleconference - March 24 | Terry Greaves reviewed the second report circulated by Dana detailing their analysis of five different bearings: 1) recent batch with tin flash. 2) recent batch with no flash. 3) old style tin/lead flash dated 2002. 4) old style, 2001. 5) old style 2000.
EDS mapping of the layers showed tin migration with the greatest migration shown by the oldest bearings.
Decision made to set aside 10 sets of unflashed rod and main bearings for possible testing
2004-04-01 | Teleconference - April 2 | Decision made to run references with unflashed rod and main bearings
2004-06-01 | TEI receives 62GB2404 unflashed rod bearings and 62GB412 unflashed main bearings and distributes to the labs | One test completes with 27 lead
2004-07-01 |  | Two additional tests complete with 7 and 9 lead
2004-07-01 | Teleconference - July 30 | Formed task group to look at operational data to try and explain differences seen in results.
2004-08-01 | Operational Review Meetings - August 20, 24, and 31 | Developed proposal for September Surveillance Panel meeting
2004-09-01 | Meeting in Richmond - September 10 | Accepted correction equation for use with 62GB2403 bearings
2004-11-01 | Meeting in Paulsboro - November 22 | Reviewed results of two calibration runs on 62GB2403 bearings. Test results more severe. Decision to re-evaluate correction equation and to analyze bearings for any changes. TEI to send bearing sets to Lubrizol and Dana for analysis.
2004-12-01 | Teleconference - December 2 | Correction equation reevaluated and new equation adopted effective 12/3/04
2005-01-01 | Meeting in San Antonio - January 12 | Jim Matasic – LZ looked at bearings and saw higher tin, At 10nm 60/40 tin – lead, 20nm 70/30 and 40nm 80/20.All measurements taken in flash coat. Much higher tin content than seen earlier. Analysis March 2004 – 80/20 lead-tin. New bearings now look like “original” T-10 bearings.
Dana analysis is 65/35 lead-tin with no gradient through flash layer.
Lubrizol to prepare a summary of all comparative bearing analysis done by them along with how data generated and meaning of data. May switch bearings with Dana.
2005-02-01 | Meeting in San Antonio - February 22 | Follow-up discussion from the January meeting. Decision made to put together timeline of events.